## Sprint 25 DVF Risks
Assumptions | Importance (1-10) | Uncertainty (1-10) | Risk Factor (Importance x Uncertainty) | Risky Assumption Test
ASAF can be deployed in a real OT/ICS or GovCloud environment without causing downtime | 10 | 7 | 70 | Execute controlled Phase 0 deployment using GovCloud Runbook and measure stability, deployment time, and failure points
Post-quantum cryptographic attestations will not introduce unacceptable latency or system overhead | 9 | 6 | 54 | Benchmark PQC signing and verification time during validation run and record CPU/memory impact
Deployment runbook can be executed by another engineer without founder intervention | 9 | 8 | 72 | Provide runbook to external DevOps engineer and observe whether deployment succeeds without undocumented steps
Defense contractors perceive $5K-$50K pricing as rational relative to CMMC failure risk | 8 | 6 | 48 | Conduct pricing validation interviews with operators and executives to test willingness-to-pay framing
DAG-based attestation outputs will be accepted by C3PAO assessors as valid audit evidence | 10 | 8 | 80 | Conduct structured feedback session with C3PAO advisor reviewing sample attestation output
Teams will use ASAF during real delivery pressure rather than bypassing it | 9 | 9 | 81 | Run pilot scenario under deadline conditions and observe behavioral usage vs avoidance
Live deployment will convert into paid contract or long-term engagement | 10 | 9 | 90 | Convert first successful pilot into paid engagement or signed LOI within defined time window
PQC and compliance scanning integrates cleanly with Platform One / Iron Bank hardened containers | 8 | 7 | 56 | Deploy containerized build into hardened baseline environment and verify compatibility
Internal key handling and artifact sealing process meets enterprise security expectations | 8 | 6 | 48 | Security review of key management artifacts and FIPS build process with external security engineer
Free scanner funnel converts qualified prospects into booked consultations | 7 | 7 | 49 | Launch scanner landing page experiment and measure consultation booking conversion rate