## Experiment Loop Continuity Spr
Experiment Loop Continuity: Sprints 19–21
Company: SecRed Knowledge Inc. (dba NouchiX / SouHimBou AI)
Product: AdinKhepra Protocol
Cross-Sprint Trend Summary (19 → 21)
Dimension | Sprint 19 | Sprint 20 | Sprint 21
Problem Clarity | ✅ Validated | — | —
Decision Clarity | ✅ Validated | — | —
Willingness to Pilot | — | ✅ Strong | ✅ Sustained
Deployment Execution | — | ❌ Blocked | ❌ Deferred
Partner Trust | — | ✅ High | ✅ Durable
Core Constraint | Message | Readiness | Readiness
Regression Analysis
What regressed?
Execution capability lagged behind market demand.
What did NOT regress?
Interest
Trust
Willingness to engage
Perceived value
Interpretation
This is a capacity bottleneck, not a market failure.

## Experiment Loop Status (End of
Loop State:
🔁 Pre-Deployment Validation → Readiness Hardening
Validated
Problem
Audience
Value
Willingness to pilot
Partner patience
Unvalidated (but isolated)
Live deployment under pressure
Next Sprint Focus (Sprint 22+)
Deployment pipeline stabilization
“Deployment-ready” definition
First time-boxed live pilot
One-Line Progression Narrative
The project progressed from message clarity (Sprint 19), to strong execution-layer demand without deployment (Sprint 20), to validated partner persistence and trust despite readiness delays (Sprint 21), isolating deployment readiness as the sole remaining gating constraint.

## Sprint 19 — Decision Clarity Va
Primary Risk Tested
Prospects understand what the product is, who it is for, and what to do next when positioned as an executive risk-elimination infrastructure (not consulting).
Experiment Type
Message comprehension + customer discovery conversations.
Experiment Design
Outcome-driven positioning (risk elimination vs features)
Clear “next action” framing
Executive language vs technical jargon
Evidence Observed
Prospects correctly articulated:
The problem being solved (audit breakdown during execution)
The target user (operators, compliance owners, delivery teams)
The next step (pilot / validation, not “learn more”)
Reduced clarification questions
Increased intent-signaling responses
Outcome
✅ Hypothesis validated.
Decision Taken
Advance from problem clarity → execution validation.
Trend Signal
📈 Positive progression
From confusion → decision clarity
Residual Risk
Understanding ≠ usage under pressure.
Next Constraint Identified
Will teams actually deploy during delivery?

## Sprint 20 — Execution-Pressure
Sprint 20 — Execution-Pressure Validation (Attempted)
Primary Risk Tested
Engineering and operator teams will deploy AdinKhepra during real delivery pressure instead of reverting to undocumented shortcuts.
Experiment Type
Pilot partner engagement (execution + live system environments).
Experiment Design
Two parallel pilot paths:
1. Execution Partner (delivery firm)
2. Operator Case Study (live MVP system)
Evidence Observed
Execution partner explicitly validated:
Dependency drift
Documentation collapse
Velocity > traceability tension
Operator accepted pilot / case study instead of cash
Both partners:
Willing to deploy
Willing to expose real systems
Willing to formalize pilot intent
Critical Interruption
❌ Deployment did not occur due to:
Internal testing gaps
Deployment pipeline instability
Packaging/readiness constraints
Outcome
⚠️ Hypothesis not falsified, but not executed.
Decision Taken
Do not force deployment → treat readiness as a gating experiment.
Trend Signal
📈📉 Mixed signal
Demand ↑
Execution readiness ↓
Regression Identified
Internal capability lag vs market pull.
Next Constraint Identified
Deployment readiness (not desirability, not trust).

## Sprint 21 — Pre-Deployment Pers
Sprint 21 — Pre-Deployment Persistence & Readiness Validation
Primary Risk Tested
Partner demand persists even when deployment is delayed due to internal readiness constraints.
Experiment Type
Partner persistence + pre-deployment value testing.
Experiment Design
Continued engagement without deployment
Shared artifacts instead of binaries:
Technical briefs
Validation frameworks
Partnership structures
Tested patience, trust, and alignment
Evidence Observed
Pilot Partner (Operator)
Accepted staged validation
Remained engaged post-delay
Willing to resume once ready
Strategic Partnership (PE / Infrastructure)
JV and financing discussions continued
Explicit agreement: pilot before scale
No pressure to rush deployment
Third-Party Validation Partner
Accepted validation role without live deployment
Value placed on audit trails & evidence integrity
Capital / Funding Interactions
Continued inbound interest
No dependency on production deployment
Outcome
✅ Hypothesis validated.
Decision Taken
Formalize pre-deployment phase as legitimate loop state.
Trend Signal
📈 Strong positive progression
Trust > immediacy
Signal durability confirmed
Regression Avoided
No loss of partners despite delay.
Next Constraint Identified
Controlled deployment readiness is now the single critical path.

## Sprint 22— Experiment Loop Map
Experiment Loop Map — Sprint 22 Rows
One-Line Label for Sprint 22 (Map Header) Sprint 22 marks the transition from validated demand to measurable deployment readiness through controlled GovCloud execution.
Row 1 — Primary Sprint 22 Experiment (REQUIRED)
Sprint:
22
Experiment Name:
GovCloud Deployment Readiness – Phase 0 Execution
Experiment Type:
Deployment Readiness / Execution Validation
Assumption Being Tested:
The AdinKhepra Protocol can be advanced from zero to a non-zero, auditable deployment state in AWS GovCloud using a documented, repeatable runbook.
Why This Assumption Is Risky:
All prior sprints validated demand, trust, and willingness to pilot, but no live deployment has occurred. Deployment readiness is the sole remaining gating constraint.
Experiment Description:
Execute Phase 0 of the GovCloud Deployment Runbook in AWS GovCloud (non-production), focusing on prerequisite and account-level setup only. Generate auditable evidence artifacts without deploying application workloads.
Metric / Success Criteria:
At least one runbook phase executed
Evidence artifacts generated (screenshots, configuration records)
OR failure documented with a clear, diagnosable blocker
Result:
TBD
Key Learning Goal:
Convert deployment readiness risk from “unknown” to “bounded and measurable.”
Decision Based on Result:
If successful → proceed to Phase 1 (Sprint 23)
If blocked → remediate identified blocker before further pilots
Trend Signal:
Expected progression from validation → execution
Next Constraint Identified:
Phase 1 GovCloud Landing Zone or specific operational blocker
Assumption Status After Experiment:
ACTIVE → Expected to move toward RETIRED
Row 2 — Supporting Experiment (Optional, but Strong)
Sprint:
22
Experiment Name:
Deployment Evidence Artifact Validation
Experiment Type:
Auditability / Evidence Validation
Assumption Being Tested:
Deployment readiness can be demonstrated through auditable infrastructure evidence prior to application deployment.
Why This Assumption Is Risky:
Without evidence artifacts, deployment progress cannot be verified or reused for compliance, partner trust, or future audits.
Experiment Description:
Capture and store all evidence artifacts generated during Phase 0 execution (access confirmations, account settings, compliance prerequisites).
Metric / Success Criteria:
Evidence artifacts captured and organized
Artifacts are reviewable without founder explanation
Result:
TBD
Key Learning Goal:
Validate that deployment progress is externally verifiable and reusable.
Decision Based on Result:
Confirm evidence standards for future phases and partner pilots.
Trend Signal:
Infrastructure maturity ↑
Next Constraint Identified:
Evidence standardization for Phase 1+
Assumption Status After Experiment:
ACTIVE
Row 3 — Supporting Experiment (Optional, Internal Control)
Sprint:
22
Experiment Name:
Deployment Time & Friction Baseline
Experiment Type:
Operational Measurement
Assumption Being Tested:
Deployment readiness can be executed within a reasonable, schedulable time window.
Why This Assumption Is Risky:
If readiness requires excessive manual effort, future pilots and scaling will stall.
Experiment Description:
Measure time, friction points, and manual interventions required to complete Phase 0.
Metric / Success Criteria:
Time-to-complete Phase 0 recorded
Friction points documented
Result:
TBD
Key Learning Goal:
Establish a baseline for repeatable deployment planning.
Decision Based on Result:
Define “deployment-ready” threshold for Sprint 23.
Trend Signal:
Execution predictability ↑
Next Constraint Identified:
Automation or documentation gaps
Assumption Status After Experiment:
ACTIVE

## Sprint 23 -Experiment Loop Map
🚀 Sprint 23 — Structural Integrity Collapse & Rebuild | Sprint 23 -📊 Updated Experiment Loop Map Rows
| Sprint | Hypothesis | Experiment | Metric | Position Target | Velocity | Acceleration
Strategic Objective | 23A | Critical vulnerabilities can be eliminated | Remove P0 issues | CRITICAL count | 0.7 | 0.8 | 0.5
| 23B | Mock data can be purged from production paths | Replace supabase mocks | “mock” count < 15 | 0.6 | 1.0 | 0.8
Transform AdinKhepra from: | 23C | PQC signatures become real | Implement Dilithium signing | No placeholder signatures | 0.7 | 0.8 | 0.5
| 23D | DAG trust boundary is real | Prevent fake scan data injection | DAG integrity test pass | 0.8 | 0.8 | 0.5
“Conceptually audit-defensible”
into:
“Cryptographically and operationally non-forgeable”
Sprint 23 is not validation.
It is integrity restoration.
🎯 Assumptions Targeted in Sprint 23 (Updated)
We are no longer testing discovery assumptions.
We are testing:
A6 — The product can be safely deployed
Now constrained by:
14 CRITICAL findings
21 HIGH findings
A7 — The deployment pipeline is trustworthy
Now constrained by:
Mock data
Backdoors
Fake signatures
A9 — Deployment does not introduce systemic security risk
Now explicitly falsified unless P0 items are resolved.
A10 — Live deployment can convert to revenue
Blocked until CRITICAL = 0.
🔱 Sprint 23 = Remediation + Re-Audit Loop
You now run this sprint in three phases.
Phase 1 — P0 Containment (Security Triage)
Must be completed before any external pilot.
Immediate Removals:
Remove khepra-dev-key backdoor
Remove hardcoded realm signing keys
Implement real JWT signature verification
Implement mTLS certificate extraction
Fix SSH host key verification
Expected Outcome:
CRITICAL findings reduced from 14 → ≤ 8 (minimum)
Position / Velocity Update:
Assumption 6
Position: 0.5 → 0.6
Velocity: 1.0 → 0.8
Acceleration: 1.0 → 0.5
Why?
We moved from "unknown safety" to "controlled safety."
Phase 2 — Mock Purge (Horizontal Collapse)
Target:
HZ-02 Supabase mocks
DG-03 fake DAG scan evidence
License PQC string concatenation
Goal:
No mock data in production path.
Measured By:
Grep count of “TODO”, “placeholder”, “mock”, “in production”
Reduction count from 50+ → < 15
Assumption 9 Update:
Position: 0.0 → 0.4
Velocity: 0.5 → 1.0
Acceleration: 0.5 → 0.8
This is real friction reduction.
Phase 3 — Re-Audit Using Four Dimensions
Re-run:
Top-Down
Bottom-Up
Horizontal
Diagonal
Success Threshold:
CRITICAL: 0
HIGH: < 10
MEDIUM: bounded
LOW: acceptable
If CRITICAL > 0:
Sprint 24 cannot move to pilot.

## Sprint 22-23 Derivative
Assumption # | Assumption Summary | Position | Velocity | Acceleration |  | Position (Validation State) |  |  | Learning Momentum = Velocity × Acceleration
1 | Problem is real & recognized | 1.0 | 0.0 | 0.0
2 | Audience correctly defined | 1.0 | 0.0 | 0.0 |  | Value | Meaning |  | Assumption 6 → 1.0 × 1.0 = 1.0 (highest priority)
3 | Value proposition understood | 1.0 | 0.0 | 0.0 |  | 1.0 | Fully validated / retired
4 | Willingness to pilot pre-revenue | 1.0 | 0.0 | 0.0 |  | 0.5 | Partially validated / bounded |  | Assumption 7 → 0.5 × 0.5 = 0.25
5 | Demand persists without deployment | 1.0 | 0.0 | 0.0 |  | 0.0 | Unknown / unvalidated
6 | Product can be deployed live | 0.5 | 1.0 | 1.0 |  | -1.0 | Invalidated |  | Assumption 8 → 0.0 × 0.0 = 0.0
7 | Deployment pipeline is repeatable | 0.5 | 0.5 | 0.5
8 | Teams deploy under pressure | 0.0 | 0.0 | 0.0 |  |  |  |  | This instantly tells us what Sprint 23 must attack.
9 | Deployment friction doesn’t negate value | 0.0 | 0.5 | 0.5 |  | Velocity (Rate of Learning)
10 | Deployment converts to revenue | 0.0 | 0.0 | 0.0
11 | Heavy education required | -1.0 | 0.0 | 0.0 |  | Value | Meaning
12 | Enterprise branding required | -1.0 | 0.0 | 0.0 |  | +1.0 | Strong positive learning this sprint
[6 empty] | +0.5 | Moderate positive learning
What Sprint 22 Changed | [5 empty] | 0.0 | No learning movement
[6 empty] | -0.5 | Negative learning
Assumptions 6 & 7 moved from static unknown → bounded and accelerating | [5 empty] | -1.0 | Strong regression
Assumption 9 gained velocity (internal friction now observable)
Acceleration (Change in Velocity)
No premature movement on downstream assumptions (8, 10)
[6 empty] | Value | Meaning
Why This Is Correct | [5 empty] | +1.0 | Learning rate accelerating
[6 empty] | +0.5 | Learning rate improving
Sprint 22 produced execution evidence, not behavioral evidence | [5 empty] | 0.0 | Stable / unchanged
[6 empty] | -0.5 | Learning slowing
Velocity > Position is the correct signal at this stage | [5 empty] | -1.0 | Learning collapsing
Acceleration > 0 proves the system is now learnable
Sprint 22 increases the velocity and acceleration of deployment-related assumptions without prematurely forcing validation of downstream behaviors.
Derivative Targets (Sprint 23) |  |  |  |  | 🚧 Sprint 23 Governing Constraint
Assumption | Position | Velocity | Acceleration |  | Four-Dimensional Audit reports:
6 | 0.6 | 0.8 | 0.5
7 | 0.7 | 0.8 | 0.5 |  | CRITICAL = 14
8 | 0.0 | 0.0 | 0.0 |  | HIGH = 21
9 | 0.4 | 1.0 | 0.8 |  | MEDIUM = 13
10 | 0.0 | 0.0 | 0.0 |  | LOW = 8
Note: Assumptions 8 and 10 remain frozen until CRITICAL = 0. |  |  |  |  | Thus:
Deployment Safety Ceiling=1−CRITICALCRITICALmax\text{Deployment Safety Ceiling} = 1 - \frac{CRITICAL}{CRITICAL_{max}}Deployment Safety Ceiling=1−CRITICALmax​CRITICAL​
We assume:
CRITICALmax = 14
If we reduce CRITICAL to ~6:
SafetyCeiling≈1−614=0.57Safety Ceiling ≈ 1 - \frac{6}{14} = 0.57SafetyCeiling≈1−146​=0.57
Thus Assumption 6 cannot exceed ~0.6 in Position during Sprint 23.
That mathematically caps Position = 0.6.
🔱 Sprint 23 Derivation by Assumption
Assumption 6 — Reliable Deployment
Logic
Audit exposes severe trust violations.
Remediation eliminates immediate backdoors.
Deployment still not externally tested.
Position Derivation
Start: 0.5
Audit Gate reduces theoretical max to ~0.6
P23=0.5+0.1=0.6P_{23} = 0.5 + 0.1 = 0.6P23​=0.5+0.1=0.6
Velocity Derivation
Sprint 22: Velocity = 1.0
Sprint 23 shifts from exploration → controlled remediation
Velocity slightly stabilizes:
V23=0.8V_{23} = 0.8V23​=0.8
Acceleration Derivation
Acceleration reduces because learning rate stabilizes.
A23=0.5A_{23} = 0.5A23​=0.5
Final:
¦ 6 ¦ 0.6 ¦ 0.8 ¦ 0.5 ¦
Assumption 7 — Repeatable Pipeline
Logic
Runbook exists.
Mock purge + auth fixes increase structural integrity.
Repeatability measurable, but not externally proven.
Position:
0.5+0.2=0.70.5 + 0.2 = 0.70.5+0.2=0.7
Velocity increases because remediation creates reproducibility data.
V=0.8V = 0.8V=0.8
Acceleration stabilizes:
A=0.5A = 0.5A=0.5
Final:
¦ 7 ¦ 0.7 ¦ 0.8 ¦ 0.5 ¦
Assumption 8 — Teams Deploy Under Pressure
Governing Rule
If CRITICAL > 0:
P8=0P_8 = 0P8​=0 V8=0V_8 = 0V8​=0 A8=0A_8 = 0A8​=0
Because you cannot ethically test pressure behavior on an insecure system.
Final:
¦ 8 ¦ 0.0 ¦ 0.0 ¦ 0.0 ¦
Assumption 9 — Friction Risk
Logic
Sprint 22 gave internal friction data.
Sprint 23 removes mock data + fake alerts → reduces structural friction.
Position:
0.0+0.4=0.40.0 + 0.4 = 0.40.0+0.4=0.4
Velocity:
High, because remediation reveals immediate signal.
V=1.0V = 1.0V=1.0
Acceleration:
Still increasing due to collapsing mock layer.
A=0.8A = 0.8A=0.8
Final:
¦ 9 ¦ 0.4 ¦ 1.0 ¦ 0.8 ¦
Assumption 10 — Revenue Conversion
Cannot move until:
CRITICAL=0CRITICAL = 0CRITICAL=0
Thus frozen.
Final:
¦ 10 ¦ 0.0 ¦ 0.0 ¦ 0.0 ¦
📊 Final Sprint 23 Derivative Targets
[5 empty] | Assumption | Position | Velocity | Acceleration
[5 empty] | 6 | 0.6 | 0.8 | 0.5
[5 empty] | 7 | 0.7 | 0.8 | 0.5
[5 empty] | 8 | 0.0 | 0.0 | 0.0
[5 empty] | 9 | 0.4 | 1.0 | 0.8
[5 empty] | 10 | 0.0 | 0.0 | 0.0
🧠 System-Level Interpretation
Sprint 23 is a stabilization sprint, not an expansion sprint.
Mathematically:
Velocity decreases slightly (from exploration to controlled refinement)
Acceleration decreases (learning curve flattening)
Position increases modestly (structural risk reduced)

## Risky Assumption Sprint 19-23
Assumption Status: Sprints 19–21 |  |  |  | Trend Function Derivatives — Updated with Sprint 22
🟢 RETIRED ASSUMPTIONS (Validated) |  |  |  | Think of each assumption not as a boolean, but as a function over time.
Sprint 22 does not magically retire all deployment assumptions — instead, it changes the derivative of several of them.
These assumptions have been sufficiently validated and no longer require active testing.
🟢 RETIRED ASSUMPTIONS (Position = 1, Velocity = 0)
1. The problem is real and recognized by the target audience
These remain unchanged by Sprint 22. They are flatlined at “true”.
Assumption:
Target users experience audit failure, dependency drift, and documentation collapse during delivery. |  |  |  | Assumptions 1–5
Evidence (Sprint 19–21): |  |  |  | Problem is real
Multiple prospects independently described the same failure modes. |  |  |  | Audience is correct
Execution partners articulated the issue unprompted. |  |  |  | Value proposition is understood
Problem framing resonated across operators, advisors, and delivery teams. |  |  |  | Willingness to pilot pre-revenue
Status: ✅ Retired |  |  |  | Demand persists without deployment
Why:
Problem recognition is consistent, repeated, and cross-segment. |  |  |  | Trend Derivative (Sprint 22):
Position: Fully validated
2. The audience is correctly defined |  |  |  | Velocity: 0 (no longer moving)
Assumption: |  |  |  | Acceleration: 0
The right audience is execution-adjacent operators (engineering, compliance owners, delivery partners), not abstract “security buyers.”
✅ Sprint 22 does not touch these.
Evidence: |  |  |  | They are structurally retired.
Engagement strongest with execution and validation layers.
Advisors and financiers defer to operators for pilot signal. |  |  |  | 🟡 ACTIVE / RISKY ASSUMPTIONS — DERIVATIVE UPDATE (Sprint 22)
Conversations stalled when framed as generic security tooling. |  |  |  | This is where Sprint 22 meaningfully changes the system.
Status: ✅ Retired
Why:
Clear audience fit confirmed by engagement depth and role alignment. |  |  |  | 6. The product can be reliably deployed in live environments
Pre–Sprint 22 State:
3. The value proposition is understood without heavy explanation |  |  |  | Position: Unknown
Assumption: |  |  |  | Velocity: 0
Prospects can understand the product and next step without lengthy education.
Acceleration: 0
Evidence:
Sprint 22 Effect:
Reduced clarification questions after Sprint 19 positioning.
Introduction of GovCloud Deployment Runbook
Prospects accurately restated the “law vs reality” gap.
Execution of Phase 0 (or attempt)
Clear acceptance of pilot / validation as next step.
Updated Trend Derivative:
Status: ✅ Retired
Why: |  |  |  | Position: Still unvalidated
Message comprehension reached consistency threshold.
Velocity: Positive (↑)
Acceleration: Positive (↑↑)
4. Prospects are willing to pilot pre-revenue
Interpretation:
Assumption: |  |  |  | Deployment risk is no longer static. It is now actively collapsing.
Early users will engage in pilots or case studies without immediate payment.
Status: ⚠️ Active → In Motion
Evidence: |  |  |  | (Expected to retire in Sprint 23 if Phase 1 executes)
Operator accepted case study instead of paid engagement.
Validation partner accepted license-for-assessment exchange. |  |  |  | 7. The deployment pipeline is repeatable and scalable
No drop-off after pilot framing. |  |  |  | Pre–Sprint 22 State:
Status: ✅ Retired |  |  |  | Position: Unknown
Why:
Multiple independent confirmations across partner types. |  |  |  | Velocity: 0
Sprint 22 Effect:
5. Demand persists even without immediate deployment |  |  |  | Runbook converts implicit knowledge into explicit steps
Assumption: |  |  |  | Time, friction, and blockers are now observable
Interest is durable and not purely time-sensitive.
Updated Trend Derivative:
Evidence (Sprint 21):
Position: Still unvalidated
Partners remained engaged despite deployment delay.
Velocity: Positive (↑)
No disengagement or loss of trust observed.
Acceleration: Neutral → Positive
Continued scheduling and follow-ups.
Interpretation:
Status: ✅ Retired |  |  |  | Repeatability is now measurable, even if not yet proven.
Why:
Persistence through delay confirms non-fragile demand. |  |  |  | Status: ⚠️ Active → Bounded Risk
🟡 ACTIVE / RISKY ASSUMPTIONS (Not Yet Validated) |  |  |  | 8. Teams will deploy during real delivery pressure
These assumptions remain live risks and should anchor future sprints. |  |  |  | Pre–Sprint 22 State:
Position: Unknown
6. The product can be reliably deployed in live environments |  |  |  | Velocity: 0
Assumption: |  |  |  | Sprint 22 Effect:
AdinKhepra can be deployed cleanly in non-production and production systems.
Still not tested (no external team deployment yet)
Evidence:
Updated Trend Derivative:
Deployment attempted but paused due to internal readiness.
Position: Unknown
No live deployment completed yet.
Velocity: 0
Status: ⚠️ Active Risk
Why: |  |  |  | Acceleration: 0
No real-world deployment evidence exists yet.
Interpretation:
Sprint 22 correctly does not touch this assumption.
It remains downstream of live pilot execution.
7. The deployment pipeline is repeatable and scalable
Status: ⚠️ Active → Deferred by design
Assumption:
Deployment can be repeated across environments without founder intervention.
Evidence: |  |  |  | 9. Deployment does not introduce friction that negates value
Pipeline instability identified. |  |  |  | Pre–Sprint 22 State:
Testing and packaging still in progress. |  |  |  | Position: Unknown
Status: ⚠️ Active Risk |  |  |  | Velocity: 0
Why:
Operational scalability unproven. |  |  |  | Sprint 22 Effect:
Internal friction now observable (Phase 0 timing, blockers)
8. Teams will deploy during real delivery pressure |  |  |  | Updated Trend Derivative:
Assumption: |  |  |  | Position: Unknown
When deadlines hit, teams will use the tool instead of bypassing it.
Velocity: Slightly positive (↑)
Evidence:
Acceleration: Low
Strong verbal agreement, no behavioral proof yet.
Interpretation:
Deployment delay prevents this test. |  |  |  | You now have internal friction data, but not user-facing friction data yet.
Status: ⚠️ Active Risk |  |  |  | Status: ⚠️ Active → Internally bounded
Why:
Execution under pressure is the core untested behavior.
10. Live deployment converts to revenue or long-term contracts
9. Deployment does not introduce friction that negates value |  |  |  | Pre–Sprint 22 State:
Assumption: |  |  |  | Position: Unknown
The act of deploying does not slow teams enough to reduce adoption.
Velocity: 0
Evidence:
Sprint 22 Effect:
Not yet observable.
No live deployment → no monetization test
Pending first live pilot.
Updated Trend Derivative:
Status: ⚠️ Active Risk
Why: |  |  |  | Position: Unknown
Usability under time constraints remains unknown.
Velocity: 0
Acceleration: 0
10. Live deployment converts to revenue or long-term contracts
Interpretation:
Assumption: |  |  |  | Correctly untouched. This is 2–3 derivatives downstream.
Successful pilots lead to paid usage, renewals, or partnerships.
Status: ⚠️ Active → Future-dependent
Evidence:
Financing and JV discussions exist.
🔴 INVALIDATED ASSUMPTIONS (No Change)
No closed revenue tied to deployment yet.
11–12
Status: ⚠️ Active Risk
Why: |  |  |  | Heavy education required
Monetization remains downstream of deployment.
Enterprise branding required
Trend Derivative:
🔴 EXPLICITLY DE-RISKED (No Longer Relevant)
Position: False
These assumptions were surfaced early but are no longer on the path.
Velocity: 0
Acceleration: 0
11. The market requires heavy education to understand the problem
These remain removed from the system.
Status: ❌ Invalidated
Why:
Prospects already feel the pain; over-education slows momentum.
Assumption Portfolio — Derivative Summary (Post Sprint 22)
|  |  |  | Category | Count | Trend Meaning
12. Trust requires enterprise branding or logos |  |  |  | Retired | 5 | Flatlined, stable
|  |  |  | Active (Moving) | 3 (6,7,9) | Velocity now positive
Status: ❌ Invalidated |  |  |  | Active (Deferred) | 2 (8,10) | Intentionally untouched
Why: |  |  |  | Invalidated | 2 | Removed
Trust emerged from clarity, rigor, and validation structure.
Key System-Level Insight (Very Important)
Assumption Portfolio Summary |  |  |  | Sprint 22 does not retire deployment assumptions —
it changes their first and second derivatives.
Category | Count
Retired Assumptions | 5 |  |  | In plain English:
Active / Risky Assumptions | 5
Invalidated / Removed | 2 |  |  | Before Sprint 22, deployment risk was static and unknowable.
After Sprint 22, deployment risk is dynamic, measurable, and schedulable.
Guidance for Experiment Loop Map |  |  |  | That is real progress, even without a live pilot yet.
For your Excel:
Mark Assumptions 1–5 as RETIRED |  |  |  | One-Line Update for Your Experiment Loop Map
Mark Assumptions 6–10 as ACTIVE |  |  |  | Sprint 22 converts deployment readiness from a static unknown into a measurable, progressing variable, increasing the velocity of execution-related assumptions without prematurely testing downstream behaviors.
Remove 11–12 from future loops
What This Means for Sprint 23 (Preview)
Forward-Looking Anchor (Sprint 22+) |  |  |  | Sprint 23 is now forced (by the derivatives) to:
All future experiments should collapse toward deployment readiness and live usage under pressure. No additional problem or audience validation is required. |  |  |  | Retire Assumption 6 (live deployment)
Begin applying pressure to Assumptions 8 and 9
Keep Assumption 10 deferred until behavior exists
Assumption Status: Sprints 19–23 - Trend Function Derivatives — Updated with Sprint 22 + Sprint 23 (Audit Gate)
Think of each assumption not as a boolean, but as a function over time.
Sprint 22 did not retire deployment assumptions — it changed their derivatives.
Sprint 23 introduces an audit gate based on the KHEPRA Protocol Audit Framework (PAIF) and the Four-Dimensional Audit baseline.
New gating rule:
✅ External pilot and revenue experiments cannot begin until CRITICAL findings = 0.
🟢 RETIRED ASSUMPTIONS (Validated)
These assumptions have been sufficiently validated and no longer require active testing.
🟢 Retired Assumptions (Position = 1.0, Velocity = 0.0, Acceleration = 0.0)
Assumptions 1–5 remain unchanged through Sprint 22 and are structurally “flatlined true.”
1) The problem is real and recognized by the target audience
Assumption: Target users experience audit failure, dependency drift, and documentation collapse during delivery.
Evidence (Sprints 19–21):
Multiple prospects independently described the same failure modes.
Execution partners articulated the issue unprompted.
Problem framing resonated across operators, advisors, and delivery teams.
Status: ✅ Retired
Why: Problem recognition is consistent, repeated, and cross-segment.
Derivatives: Position 1.0 ¦ Velocity 0.0 ¦ Acceleration 0.0
2) The audience is correctly defined
Assumption: The right audience is execution-adjacent operators (engineering, compliance owners, delivery partners), not abstract “security buyers.”
Evidence:
Engagement strongest with execution and validation layers.
Advisors and financiers defer to operators for pilot signal.
Conversations stalled when framed as generic security tooling.
Status: ✅ Retired
Why: Clear audience fit confirmed by engagement depth and role alignment.
Derivatives: Position 1.0 ¦ Velocity 0.0 ¦ Acceleration 0.0
3) The value proposition is understood without heavy explanation
Assumption: Prospects can understand the product and next step without lengthy education.
Evidence:
Reduced clarification questions after Sprint 19 positioning.
Prospects accurately restated the “law vs reality” gap.
Clear acceptance of pilot / validation as next step.
Status: ✅ Retired
Why: Message comprehension reached consistency threshold.
Derivatives: Position 1.0 ¦ Velocity 0.0 ¦ Acceleration 0.0
4) Prospects are willing to pilot pre-revenue
Assumption: Early users will engage in pilots or case studies without immediate payment.
Evidence:
Operator accepted case study instead of paid engagement.
Validation partner accepted license-for-assessment exchange.
No drop-off after pilot framing.
Status: ✅ Retired
Why: Multiple confirmations across partner types.
Derivatives: Position 1.0 ¦ Velocity 0.0 ¦ Acceleration 0.0
5) Demand persists even without immediate deployment
Assumption: Interest is durable and not purely time-sensitive.
Evidence (Sprint 21):
Partners remained engaged despite deployment delay.
No disengagement or loss of trust observed.
Continued scheduling and follow-ups.
Status: ✅ Retired
Why: Persistence through delay confirms non-fragile demand.
Derivatives: Position 1.0 ¦ Velocity 0.0 ¦ Acceleration 0.0
🟡 ACTIVE / RISKY ASSUMPTIONS (Not Yet Validated)
These assumptions remain live risks and should anchor future sprints.
Sprint 22 moved deployment risks from static → measurable.
Sprint 23 introduces audit reality: the codebase is not production-ready until CRITICAL issues are eliminated.
6) The product can be reliably deployed in live environments
Assumption: AdinKhepra can be deployed cleanly in non-production and production systems.
Evidence (Sprints 20–22):
Deployment attempted but stalled due to internal readiness.
GovCloud Runbook introduced measurable execution steps.
New Evidence (Audit):
Four-Dimensional Audit identifies CRITICAL security gaps blocking production deployment (e.g., hardcoded keys, dev key bypass, JWT/mTLS gaps).
Status: ⚠️ Active Risk → Audit-Gated
Why: Live deployment cannot proceed until CRITICAL = 0.
Derivatives: Position 0.5 ¦ Velocity 1.0 ¦ Acceleration 1.0
Sprint 23 Target: Position 0.6 ¦ Velocity 0.8 ¦ Acceleration 0.5
(Containment + measurable remediation)
7) The deployment pipeline is repeatable and scalable
Assumption: Deployment can be repeated across environments without founder intervention.
Evidence:
Pipeline instability identified; packaging/testing in progress.
Runbook makes steps explicit and observable.
New Evidence (Audit):
System contains >50 “in production…” deferrals; mocks in production paths; signature and licensing chain integrity gaps.
Status: ⚠️ Active Risk → Bounded but unproven
Why: Repeatability requires removing stubs/mocks and stabilizing core auth + signing.
Derivatives: Position 0.5 ¦ Velocity 0.5 ¦ Acceleration 0.5
Sprint 23 Target: Position 0.7 ¦ Velocity 0.8 ¦ Acceleration 0.5
8) Teams will deploy during real delivery pressure
Assumption: When deadlines hit, teams will use the tool instead of bypassing it.
Evidence: Strong verbal agreement; no behavioral proof yet.
Status: ⚠️ Active Risk → Deferred
Why: Cannot be tested until deployment is safe (CRITICAL = 0) and a pilot is live.
Derivatives: Position 0.0 ¦ Velocity 0.0 ¦ Acceleration 0.0
Sprint 23 Target: No change (blocked until audit gate passes)
9) Deployment does not introduce friction that negates value
Assumption: Deploying the tool does not slow teams enough to reduce adoption.
Evidence (Sprint 22):
Internal friction now observable via runbook execution timing and blockers.
New Evidence (Audit):
Mock data and “fake-but-looks-real” behaviors introduce major operational trust friction (dashboards, evidence, alerts, scans).
Status: ⚠️ Active Risk → Integrity Friction Identified
Why: Adoption depends on removing fake evidence and no-op alerts before exposing operators.
Derivatives: Position 0.0 ¦ Velocity 0.5 ¦ Acceleration 0.5
Sprint 23 Target: Position 0.4 ¦ Velocity 1.0 ¦ Acceleration 0.8
10) Live deployment converts to revenue or long-term contracts
Assumption: Successful pilots lead to paid usage, renewals, or partnerships.
Evidence: Financing + JV discussions exist; no closed revenue tied to deployment.
Status: ⚠️ Active Risk → Frozen downstream
Why: Monetization cannot be tested until pilot is safe and real (CRITICAL = 0).
Derivatives: Position 0.0 ¦ Velocity 0.0 ¦ Acceleration 0.0
Sprint 23 Target: No change (blocked until audit gate passes)
🔴 EXPLICITLY DE-RISKED (No Longer Relevant)
11. Heavy education required → ❌ Invalidated
12. Enterprise branding required → ❌ Invalidated
Derivatives: Position -1.0 ¦ Velocity 0.0 ¦ Acceleration 0.0
Assumption Portfolio — Derivative Summary (Post Sprint 22 + Sprint 23 Gate)
Category | Count | Trend Meaning
Retired | 5 | Flatlined, stable
Active (Moving) | 3 (6,7,9) | Velocity positive; now audit-gated
Active (Deferred/Frozen) | 2 (8,10) | Blocked until CRITICAL = 0
Invalidated | 2 | Removed
Key System-Level Insight (Updated)
Sprint 22 turned deployment from unknowable to measurable.
The Four-Dimensional Audit reveals the current system contains trust-breaking defects (mock evidence, placeholder signatures, auth gaps).
Therefore Sprint 23 is forced to become:
A remediation + re-audit sprint, not a pilot sprint.
The gating metric is CRITICAL findings reduced to 0.
Updated Derivative Targets (Sprint 23)
Assumption | Position | Velocity | Acceleration
6 | 0.6 | 0.8 | 0.5
7 | 0.7 | 0.8 | 0.5
8 | 0.0 | 0.0 | 0.0
9 | 0.4 | 1.0 | 0.8
10 | 0.0 | 0.0 | 0.0
Note: Assumptions 8 and 10 remain frozen until CRITICAL = 0.